## For Website_ENG
Donors’ supported Projects Envisaged in the State Budget
As of May 31, 2020 (In thousand)
Projects | Date of Agreement* | Project Closing date | Agreed amount |  |  | Amount envisaged in the State Budget 2020 |  | Expenditures made during the Year of 2020 (Actual expenditures) ** |  | Total of Expenditures (Actual expenditures) ** |  | Comment
|  |  | Currency of Loan/Grant |  |  | GEL |  | GEL |  | GEL
|  |  | Currency | Credit | Grant | Credit | Grant | Credit | Grant | Credit | Grant
Road Infrastructure | [5 empty] | 592180 | 5000 | 257137.3036 | 1941.3167 | 2839950.8406 | 40388.3833
Fourth East-West Highway Improvement Project (Agara - Zemo Osiauri) (WB) | 2013-06-06 | 2019-12-31 | SDR | 24500 |  | 400 |  | 233.0821 |  | 163860.9467 |  | - Construction of the Agara - Zemo Osiauri Section (approximately 12 km) of the Highway (construction works are completed, 7 km section is open for traffic, the remaining 5 km section will be opened after the completion of construction works on the section of Zemo Osiauri-Chumateleti Lot I) - Construction of a riverbank protection (approximately 3.4 km) structure (completed); - Feasibility study and other preparatory activities (including Second Rikoti Tunnel) for the construction of the Rikoti-Zestafoni Section of Highway (completed); - Detailed project preparation works completed for Chumateleti-Khevi, Zhinvali-Larsi and Samtredia-Zugdidi-Anaklia sections; - Detailed project preparation works are ongoing for Rustavi-Red Bridge-Sadakhlo and Tbilisi-Lagodekhi sections.; - Detailed project preparation works completed for Rustavi-Red Bridge-Sadakhlo section; - Detailed project preparation works are ongoing for Tbilisi-Lagodekhi section.
|  |  | USD | 38000
East-West Highway Corridor Improvement Project (Zemo Osiauri - Rikoti) (WB, EIB) | 2016-02-10 | 2023-12-31 | USD | 140000 |  | 59300 |  | 32446.4766 |  | 200662.9676 |  | - Construction of the Zemo Osiauri - Chumateleti Section (approximately 14.1 km) of the Highway ( construction works are ongoing for Lot I, agreement for Lot II was terminated, out of which for 1.9 km section (km-5 + 800-km-7 + 700) the contract was signed with the contracting company of Lot I - Sinohydro. Completion of km7.7 is planned for the end of July 2020 and tender for the remaining part of Lot II (km7.7-km 14.6) were opened on April 1, 2020. The process of evaluating the submitted proposals is ongoing; - Institutional Development of the Roads Department (ongoing); - Technical Assistance to the Ministry of Economy and Sustainable Development of Georgia in preparation of Feasibility Study to identify priority logistic sites (completed); - Preparation of designs and supporting studies for future investment for the development of the road network (ongoing).
|  |  | EUR | 49450
Road Corridor Investment Program (Kobuleti Bypass Road) (ADB) | 2009-10-29 | 2019-09-29 | SDR | 75892 |  | 0 |  | 1489.4666 |  | 391974.5999 |  | - Construction of a new Kobuleti Bypass Road (approximately 32 km) (First section (12+400 - km 31+259) of the Highway is open for traffic, construction works completed for second section (18 km), traffic is open); - Detailed project preparation works completed for Khevi-Argveta section; - Detailed project preparation works are ongoing for Tbilisi-Natakhtari-Zhinvali section.Due to the completion of the program, the source of funding for this agreement has changed. The agreement was transferred to the constructionof the project for Khevi-Ubisa section.
|  |  | USD | 140000
Batumi New Bypass Road (ADB, AIIB) | 12.06.2017 | 30.06.2023 | EUR | 108190 |  | 56000 |  | 23190.8233 |  | 117939.5439 |  | - Construction of Batumi Bypass two-lane 14.3 km Road (construction works are ongoing); - Maintenance of approximately 200 km International and Local roads (planned); - Detailed project preparation works are ongoing for Batumi-Sarfi section.
|  |  | USD | 114000
East-West Highway Improvement Project (Zestafoni - Kutaisi - Samtredia) (JICA) | 2009-12-16 | 2023-06-24 | JPY | 22132000 |  | 130 |  | 3596.3393 |  | 400509.1677 |  | - Construction of Zestafoni - Kutaisi section (15.2 km) (Construction works are completed, the road section section is open for traffic); - Construction of a new Kutaisi bypass (Construction works completed for 17.3 km section of the Highway and was opened for traffic in 2014); - Construction of a new road from Kutaisi to Samtredia (Construction works are completed and 24 km section is open for traffic).
East-West Highway Improvement Project (Samtredia-Grigoleti-Kobuleti) (EIB, EU) | 2012-05-11 | 2019-11-28 | EUR | 200000 | 20000 | 37000 | 5000 | 14790.7394 | 1941.3167 | 368475.5921 | 40388.3833 | - Construction of a new four lane highway (approx. 50 km) from Samtredia to Grigoleti (construction works are going under the I, II and IV lots, III lot - the procedures of evaluation of submitted proposals at the pre-qualification are ongoing , the deadline for submitting applications is February 04, 2020); - The contract for Lot I was terminated and the contract for the remaining works was signed on November 13, 2018. Deadline for completion of works is December 03, 2020; - The contract for Lot II was signed on November 13, 2015. Completion of works is planned by the end of 2020; - The contract for Lot IV was signed on December 24, 2014. Completion of works is planned by the end of 2020; - Road sections of Poti-Grigoleti and Grigoleti-Kobuleti Bypass Road ( preparation of the Detailed Design was completed);
Construction-Rehabilitaion of Chumateleti-Khevi section of Tbilisi-Senaki-Leselidze Road (WB, EIB) | 04.2.2017 | 31.12.2023 | EUR | 16000 |  | 32500 |  | 2559.8254 |  | 62199.3759 |  | Upgrading of approximately 11 km of the existing 2-line East-West Highway Corridor to a 2-line dual carriageway from Chumateleti to Khevi (Mobilization, preparatory and construction works are ongoing).
| 2018-10-09 | 2021-12-09 | EUR | 250000
Construction-Rehabilitation of Ubisa-Dzirula section of Tbilisi-Senaki-Leselidze Road (EIB) | 2016-10-09 | 2021-12-09 | EUR |  |  | 84750 |  | 32047.3862 |  | 247054.3907 |  | Consturction-Rehabilitation of Khevi-Ubisa section of Tbilisi-Senaki-Leselidze Road (construction works are ongoing).
Construction of Grigoleti-Choloki (km48 - km64) section of Senaki-Poti-Sarpi Road (EIB) | [5 empty] | 42000 |  | 7914.4797 |  | 40147.2056 |  | Construction of Grigoleti-Choloki (km48 - km64) section of Senaki-Poti-Sarpi Road (constructions works are ongoing).
Construction of Rustavi-Red Bridge (km22 - km57) section of Tbilisi-Red Bridge (Border of Republic of Azerbaijan) Road (EIB) | [11 empty] | Construction of Rustavi-Red Bridge (km22 - km57) section of Tbilisi-Red Bridge (Border of Republic of Azerbaijan) (planned). (The tender procedures for selecting the supervision of construction works of Rustavi-Red Bridge (Lot 1 an Lot 2) are ongoing).
Construction/Upgrading of Algeti-Sadakhlo Road (EIB) | [11 empty] | Construction/Upgrading of Algeti-Sadakhlo Road (planned) (Tender procedures are ongoing to select a supervisor for the construction works of Algeti-Sadakhlo section).
Consturction-Rehabilitation of Khevi-Ubisa section of Tbilisi-Senaki-Leselidze Road (ADB) | 2018-10-05 | 2024-12-31 | EUR | 255297 |  | 64750 |  | 29434.7986 |  | 155060.1402 |  | Reconstruction and construction of Tbilisi-Senaki-Leselidze road Khevi Ubisa section (construction works are onging). Detailed project preparation works are ongoing for Tbilisi and Natakhtari-Zhinvali section.
Construction of road and tunnel on Kvesheti-Kobi section of Mtskheta-Stepantsminda-Larsi Road (ADB) | 2019-08-27 | 2023-12-31 | EUR | 370236 |  | 35500 |  | 1535.2173 |  | 225201.3586 |  | Construction of road and tunnel on Kvesheti-Kobi section of Mtskheta-Stepantsminda-Larsi Road. Road section: (Preparatory works are ongoing).
| 2019-10-11 |  |  | 53400
Consturction-Rehabilitation of Shorapani Argveta Section of Tbilisi-Senaki-Leselidze Road (ADB)) | 2019-11-27 | 2022-12-31 | EUR | 255100 |  | 99000 |  | 97459.358 |  | 97459.358 |  | Rehabilitation-reconstruction of Shorapani-Argveta section of Tbilisi-Senaki-Leselidze highway. The agreement was signed on January 16, 2020(Preparatory work is ongoing).
Construction of Poti Bridge on River Rioni (ADB) | [5 empty] | 0 | [5 empty] | Construction of Poti Bridge on River Rioni and the tender proposal is being evaluated on the tender for the construction of access roads.
Construction of Lochini-Sagarejo (km20-km50) section of Tbilisi-Bakurtsikhe-Lagodekhi Road (EIB) | [5 empty] | 0 | [5 empty] | Construction of Lochini-Sagarejo (km20-km50) section of Tbilisi-Bakurtsikhe-Lagodekhi Road (the procedures for identifying the funding sources are ongoing).
Second Secondary and Local Roads Project (SLRP II) (WB) | 2012-03-22 | 2019-06-30 | SDR | 25800 |  | 0 |  |  |  | 127772.7657 |  | Rehabilitation of secondary and local roads in different regions of Georgia (approx. 225 km in total) (The project was closed on June 30, 2019).
|  |  | USD | 30000
Third Secondary and Local Roads Project (SLRP III) (WB) | 2014-07-09 | 2020-06-30 | USD | 75000 |  | 11200 |  | 2977.4344 |  | 155210.4237 |  | Rehabilitation of secondary and local roads in different regions of Georgia (approx. 200 km in total) (rehabilitation works for additional 12 road sections are completed within the project (approx. 80 km in total). -6 km out of the 15.5 km section of Gurjaani bypass road has been completed, as well as the construction of 6 bridges out of 7 bridges have been completed, land and construction of artificial buildings works are ongoing..
Secondary Road Asset Management Project (WB) | 2016-03-28 | 2021-12-31 | USD | 40000 |  | 30000 |  | 209.4644 |  | 41572.8051 |  | - Rehabilitation of selected secondary road sections in Guria region (planned); - Rehabilitation of selected secondary road sections in Mtskheta - Mtianeti, Racha - Lechkhumi and Shida Kartli regions considering the design and construction conditions (rehabilitation works were completed for two sections, the contract was terminated on lots I and II. Tender proposals were opened on April 3, 2020 within the framework of the re-announced tender. The companies that won the tender have been identified, the procedures required for concluding contracts (both lots) are ongoing. -Monitoring and supervision of works contracts (supervision of rehabilitation works of 4 road sections is ongoing).
Construction-Rehabilitation of Chumateleti-Kharagauli section of Secondary Dzirula-Kharagauli-Moliti-Pona-Chumateleti Road (ADB) | 19,06,2017 | 31.08.2021 | USD | 80000 |  | 24400 |  | 6961.6987 |  | 41207.3459 |  | Rehabilitation of secondary road connecting Dzirula-Kharagauli-Moliti-Pona-Chumateleti Road ( Dzirula-Moliti road rehabilitation - the constraction works are ongoing).
Batumi (Angisa) - Rehabilitation-reconstruction of Khulo-Zarzma section of Akhaltsikhe highway.) (Kuwait Fund) | 2017-01-17 | 2020-12-31 | KWD | 8000 |  | 11250 |  | 290.7138 |  | 2357.4814 |  | Batumi (Angisa) - Rehabilitation of the Khulo-Zarzma section of the Akhaltsikhe highway has been suspended. Tender proposals were opened on April 10, 2020 within the framework of the re-announced tender. The submitted proposala are being evaluated.
Sadakhlo - Bagratashen Bridge Project (EBRD) | 2016-12-30 | 2019-12-31 | EUR | 6000 |  | 4000 |  |  |  | 1285.3718 |  | Construction of a new bridge at the Sadakhlo-Bagratashen border crossing between the Republic of Armenia and Georgia (detailed projectioon works are ongoing).
Urban and Municipal Infrastructure | [5 empty] | 178420 | 6000 | 52226.0424 | 1294.4283 | 860667.742 | 16561.2489
Second Regional and Municipal Infrastructure Development Project (WB) | 2014-08-18 | 2021-04-30 | USD | 30000 | 5000 | 8400 | 3800 | 3059.4786 | 634.9146 | 55644.7921 | 8771.7066 | Small size infrastructural projects in various regions of Georgia (rehabilitation of roads, streets, water-pipes, sewerage system) (construction works are ongoing).
Adjara Solid Waste Project (EBRD) | 2010-02-18 | 2022-12-31 | EUR | 3000 |  | 2000 |  | 1152.389 |  | 3554.1738 |  | -Construction of a new, modern solid waste landfill in Adjara (Kobuleti, near Tsetskhlauri village; Preparatory activities are ongoing); - Closure of the existing solid waste landfill in Batumi (to be closed once a new solid waste landfill becomes operational).
Kutaisi Solid Waste Project (KfW, EU) | 2013-12-13 | 2022-12-31 | EUR | 20000 | 2000 | 400 | 600 | 284.531 | 659.5136 | 7724.3897 | 7014.9367 | - Construction of a new solid waste landfill (Kutaisi entrance, Chognari Village) (preparatory works are ongoing); - Purchasing of necessary machinery/equipment for the transportation of solid waste and functioning of the sanitary landfill (planned in 2017); - Closure of the existing solid waste landfill in Kutaisi (to be closed once a new solid waste landfill becomes operational).
Sustainable Urban Transport Investment Program (ADB) | 2010-06-21 | 2020-07-18 | SDR | 68625 |  | 22800 |  | 20841.91 |  | 429386.9251 |  | - Rehabilitation of Zugdidi-Mestia road (completed); - Anaklia coastal protection Phase I (Completed); - Construction of a new subway station "University" in Tbilisi (completed); - Construction of Tbilisi-Rustavi highway Sections I - II (completed); - Construction of Tbilisi-Rustavi highway Section II (construction works are ongoing); - Coastal protection of Anaklia Phase II (completed); - Construction of a coastal protection works in Batumi (construction works are ongoing); - Rehabiliotation of subway station in Tbilisi ( replacement of subway electrical and ventilation system) (construction works are ongoing).
|  |  | USD | 141886
Second Regional Development Project (Imereti) (WB) | 2012-11-09 | 2019-12-31 | SDR | 19800 |  | 0 |  | 1368.0586 |  | 80642.1988 |  | - Rehabilitation of infrastructure in Tskaltubo; - Rehabilitation and improvement of cultural heritage sites in Imereti region (supportive infrastructure) (constructions works are ongoing).
|  |  | USD | 9000
Third Regional Development Project (Samtskhe-Javakheti and Mtskheta-Mtianeti) (WB) | 2015-08-07 | 2022-12-31 | USD | 60000 |  | 20000 |  | 3019.909 |  | 49099.9585 |  | Rehabilitation of infrastructure and improvement of cultural heritage sites in Samtskhe-Javakheti and Mtskheta-Mtianeti (construction works are ongoing).
Kvemo Kartli Solid Waste Project (EBRD, SIDA) | 2015-05-12 | 2021-05-12 | EUR | 4300 | 1843 | 420 | 300 |  |  | 967.4223 |  | Construction of new landfill in the Kvemo Kartli Region (in the city of Marneuli) (preparatory works are ongoing).
Energy Efficiency Improvements in Public Buildings and Use Renewables and Alternatuve Energy in Georgia (NEFCO , E5P) | 2018-07-04 | 2020-07-04 | EUR | 2830 | 1870 | 5000 | 1000 |  |  | 0 | 0 | Implementation of energy efficiency activities in public buildings. (Implementation of renewable and alternative energy sources in administrative and educational buildings) (preparatory works are ongoing).
Georgia Urban Reconstruction and Development FL (EIB) | 2016-02-11 | 2019-12-31 | EUR | 100000 |  | 49000 |  | 22499.7662 |  | 201987.3572 |  | - Small size infrastructural projects in various regions of Georgia (rehabilitation of roads, streets, water-pipes, sewerage system); - Rehabilitation/construction of the infrastructure damaged after the flooding in Tbilisi in 2015 (construction works are ongoing)
Georgia Upgrade of Municipal Infrastructure (EIB) | 2016-12-09 | 2021-12-31 | EUR | 100000 |  | 0 |  |  |  | 0 |  | - Small size infrastructural projects in various regions of Georgia (rehabilitation of roads, streets, water-pipes, sewerage system); - Rehabilitation/construction of the infrastructure damaged after the flooding in Tbilisi in 2015 (construction works are ongoing)
Livable Cities Investment Program (ADB) | 2019-12-06 | 2022-12-31 | EUR | 13550 |  | 8000 |  |  |  | 0 |  | The resource will mainly finance the preparatory activities of the projects planned within the framework of the "Cities for Investment Program" (Feasibility study of projects, detailed study of social and environmental conditions, preparation of design and tender documentation and other).
Urban Transport Development (EBRD) | 2019-11-29 | 2023-12-20 | EUR | 17000 |  | 15000 |  |  |  | 0 |  | To purchase 175 new buses for 6 cities (Gori, Kutaisi, Poti, Rustavi, Telavi and Zugdidi ) and rehabilitation of outdated municipal transport.
Municipal Service Improvement Program (EBRD) |  |  | EUR |  |  | 10000 |  |  |  | 0 |  | To purchase the speciial techniques for improvement of the service quality and security measures in Bakuriani.
Rehabilitation and Reconstruction of Chiatura's Gondola Lifts (France) | 2014-09-02 | 2019-12-31 | EUR | 13200 |  | 0 |  |  |  | 30687.9214 |  | Upgrade of Urban Mechanical equipment for reversible gondola ropeways for the city of Chiatura: - Gondola ropeway #1 Center - Sanatorium (construction works are ongoing); - Gondola ropeway #2 Center - Lezhubani (construction works are ongoing); - Gondola ropeway #3 Center - Naguti (construction works are ongoing); - Gondola ropeway #4 Center - Mukhadze (construction works are ongoing)
Integrated Solid Waste Management Program II (Kakheti and Samegrelo - Zemo Svaneti.) (KfW) | 2017-10-27 | 2022-12-30 | EUR | 30000 | 2000 | 400 | 300 |  |  | 477.0331 | 774.6056 | To implement a regional municipal waste management system in Zugdidi (on the existing waste management base) and Gurjaani (village Melaani) that will serve Samegrelo-Zemo Svaneti and Kakheti regions (preparatory works are ongoing).
EBRD - Tbilisi Solid Waste Project | 1900-01-26 02:41 | 1900-01-26 02:41 | EUR | 15000 |  | 37000 |  |  |  | 495.57 |  | - Renewing the Solid Waste collection fleet (rear loaded compactor vehicles); - Upgrading of the existing solid waste transfer station; - Rehabilitation and Improvement of the leachate system at the solid waste landfill of Tbilisi.
Water Infrastructure | [5 empty] | 154800 | 15250 | 58024.1537 | 1569.2315 | 961715.4985 | 115909.0232
Kobuleti Wastewater Project (EBRD, ORET) | 2008-06-27 | 2020-06-01 | EUR | 3700 | 1814 | 300 |  | 304.502 |  | 9925.2829 | 3649.681 | Rehabilitation of wastewater collector and treatment plant in Kobuleti (ongoing).
Urban Services Improvement Investment Program (Water Supply and Sewage Sector) (ADB) | 2011-05-10 | 2021-03-29 | SDR | 163600 |  | 129000 |  | 49957.418 |  | 732346.6436 |  | -Mestia - Construction of Water Intake building (completed);Construction/rehabilitation of water supply and wastewater networks (construction works are completed); Construction of wastewater treatment plant and new reservoir, rehabilitation of existing reservoir (Construction was completed; A final testing day has been set); Designing and construction of Mestia wastewater treatment plant rehabilitation (project works are ongoing); -Anaklia - Construction of Water Intake building; Construction/rehabilitation of water supply and wastewater networks (completed); construction of wastewater treatment plant (the storage procedures are ongoing); Construction/projecting of wastewater treatment plant (tendering procedures are ongoing); - Kutaisi - Construction/rehabilitation of water supply systems (reservoirs, pumping stations, water distribution network) (the acceptance procedures are ongoing); - Poti - Construction/rehabilitation of water supply systems (completed); rehabilitation of wastewater network (constructio works are ongoing); rehabilitation of wastewater treatment plant (construction works are ongoing); - Ureki - Construction of water supply and wastewater systems ( completed, the warranty period is ongoing); - Ureki - Construction of wastewater collector and treatment plant (completed, the testing process is ongoing); - Zugdidi - Construction of water systems (construction works are ongoing); - Zugdidi - Construction/rehabilitation of wastewater systems (construction works are ongoing); - Zugdidi - Construction of water supply and wastewater systems (the procedures for selection of the design are ongoing); - Jvari – Construction of Water Supply System (construction works are ongoing); - Chiatura - Construction of Water Supply System (construction works are ongoing and partial acceptance procedures are ongoing); - Marneuli - Rehabilitation of water supply and wastewater system facilities ( the mobilization works are ongoing); - Marneuli - wastewater-treatment plant designing and construction ( project works are ongoing and the mobilization process has started); - Construction of Abasha main line (constructions works are ongoing); - Construction of Water Supply System in Telavi (the procedures for preparing tender documentation is ongoing); - Construction water and sewerage systems in Gudauri (construction works are ongoing); - Constraction of wastewater treatment plant in Gudauri (project works are ongoing).
|  |  | USD | 250000
Kutaisi Waste Water (EIB, EPTATF) | 15,10,2015 | 2020-10-15 | EUR | 100 |  | 0 | 800 |  |  | 35.078 |  | Kutaisi - Construction/rehabilitation of water supply systems and treatment Plant (the procedures of designing of construction works and supervisory service procurement are ongoing).
Rehabilitation of Municipal Infrastructure Facilities in Batumi - Phase III (KfW, EU-NIF) | 2011-08-18 | 2021-12-31 | EUR | 26988.339 | 31228.536 | 1500 | 750 | 1633.6273 |  | 68083.2673 | 65489.7635 | - Rehabilitation of water supply and sewerage systems network in Batumi (activities are partially completed); - Construction/rehabilitation of water reservoirs (completed); - Construction-rehabilitation of treatment plants (completed); - Creation of a sewerage system in the coastal villages of Adjara, in particular Gonio, Kvariati, Sarfi and Akhalsofeli (completed); - Modernization of the existing water supply infrastructure and provision of decentralized water supply systems In three villages surrounding Batumi (Chakvi, Mtsvane Kontskhi and Makhinjauri) (ongoing); -Installation of water meters in Batumi (works are ongoing).
Rehabilitation of Municipal Infrastructure Facilities in Batumi - Phase IV (KfW, EU) | 2015-12-22 | 2020-06-30 | EUR | 30000 | 2000 | 24000 | 13300 | 5963.8021 | 261.2591 | 56794.3299 | 5250.4743 | Rehabilitation and extension of water supply and wastewater system facilities in Batumi (ongoing).
Water Infrastructure Modernisation Project II (EIB, EU) | 2013-08-20 | 2018-08-20 | EUR | 40000 | 8000 | 0 | 0 | 164.8043 | 33.7551 | 94530.8967 | 19355.5557 | Improvement of water supply system in various regions of Georgia (ongoing).
Supporting Sustainable Wastewater Management (SIDA) | 2013-07-25 | 2020-02-28 | USD |  | 10052.155 | 0 | 400 |  | 1274.2174 |  | 22163.5487 | Construction of the wastewater treatment plants in Tskaltubo and Telavi (construction works are ongoing).
Energy Infrastructure | [5 empty] | 44000 | 7000 | 18204.814 | 0 | 309572.1345 | 20950.6801
Enguri Hydro Power Plant Rehabilitation Project - Climate Resilience Upgrade (EBRD, EU) | 2018-01-05 | 31,12,2021 | EUR | 28000 | 7000 | 10000 | 5000 | 17057.6175 |  | 36947.3904 |  | - The project aims to make improvements to the Enguri HPP to alleviate critical power shortages in Georgia at a low cost and to enhance the environmental benefits of the Enguri HPP facility. - New EBRD loan will also help to improve the climatic conditions on the HPP territory. (preparatory works are ongoing).
Transmission Line Project - 500-220 kv "Jvari - Khorga" (EBRD, KfW, EU) | 2013-10-25 | 2018-12-29 | EUR | 60200 | 8000 | 5000 |  | 70.0995 |  | 93226.034 | 20950.6801 | - Construction of the electricity lines from the Kavkasioni Transmission Line to the Jvari substation and between the Jvari and the Khorga substations (ongoing); - Construction of Transmission Lines connecting Ksani and Stepantsminda substations (500 Kv) (ongoing) .
Transmission Line Project - 500 kv "Ksani - Stefanwminda" ( KfW). | [7 empty] | 1077.097 |  | 54338.617
250MGvar reactor in substation "Zestafoni"(EBRD) | [9 empty] | 5120.6747 |  | Constructing of 250 Mgvar capacity reactor in substation "Zestafoni 500" (planned).
Transmission Grid Strengthening Project - 220kv "Akhaltsikhe - Batumi" (WB) | 2014-09-03 | 2021-07-01 | USD | 60000 |  | 8500 |  |  |  | 118003.7259 |  | Construction of high voltage Electricity Transmission Line (220kv) from Akhaltsikhe to Batumi (142km) (ongoing). At this stage consultations are ongoing with the donor in order to replace certain works and the completion date within the project, to reflect the changes in the Loan Agreement regarding the project implementation unit due to the merging of the Ministries of Energy and Environmental Protection. The Amendment to the Agreement will be submitted to the Parliament for ratification.
Georgian Electricity Sector Development (WB) |  |  | USD | [6 empty] | 1935.6926 |  | Electricity Sector Strategic Environmental and Social Assessment.
North Ring – Tskaltubo (Phase 1) (EBRD, KfW) |  |  | EUR |  |  | 3500 |  |  |  | 0 |  | - Construction of 220kV double-circuit OHL Khudoni-Nenskra; - Construction 110kV OHL Khudoni-Mestia; - Construction of 125MVA, 110/35kV SS Mestia; - Construction of 500/220/110kV SS Khudoni; - 500kV OHL Kavkasioni tie-in to SS Khudoni; - Construction of 110kV double circuit OHL Kheledula-Jakhunderi; - Construction/Extension of 220kV SS Lajanuri (planned)
500Kv OHL Jvari –Tskhaltubo (WB) |  |  | USD |  |  | 3500 |  |  |  | 0 |  | - Construction of 500kV single-circuit OHL Jvari – Tskhaltubo (approximately 100 Km); - Construction of 500kV SS Tskhaltubo (planned)
Transmission Line Project -500 kv Tskaltubo -Akhaltsikhe - Tortumi (KfW) | 2017-04-13 | 2022-06-30 | EUR | 125000 | 9900 | 4000 | 2000 |  |  | 0 | 0 | - Construction of 500kV double-circuit OHL Tskaltubo-Akhaltsikhe) - Extension of 500kV substation Akhaltsikhe; - Construction of 400kV OHL Akhaltsikhe-Tortum (planned)
Reinforcement of Transmission Infrastructure of Guria (KfW) | [5 empty] | 4000 |  |  |  | 0 |  | - 220/110kV substation Ozurgeti, 250MVA installed capacity; - Double circuit OHL tie-in from 220kV OHL Paliastomi to 220/110kV substation Ozurgeti; - Construction of a new 110kV substation in Chokhatauri; - Construction of a new double-circuit 110kV line Ozurgeti-Chokhatauri
Kheledula-Lajanuri-Oni (KfW) | [5 empty] | 2500 |  |  |  | 0 |  | Planned
Strengthening Kakheti Infrastructureა (KfW) |  |  | EUR |  |  | 3000 |  |  |  | 0 |  | Planned
Agriculture Sector | [5 empty] | 41000 | 4000 | 4194.3566 | 2864.0671 | 87926.0332 | 13327.9666
Agriculture Modernization, Market Access, and Resilience (GEF, IFAD) | 2015-02-17 | 2020-10-17 | SDR | 8610 |  | 3400 | 4000 | 2838.5504 | 2864.0671 | 28028.7697 | 13327.9666 | support for the growth of income of small farmers in various regions of Georgia and promote investments in the production / processing / sale of agricultural products - Rehabilitation works for Tiriponi irrigation system distribution network (G-3-2-1) and rehabilitation of its other distribution networks (Shida Kartli, Gori) are ongoing; - Rehabilitation of Tirifoni irigation system (G-3 distributor's internal network) (Gori Municipality) is ongoing;
| 2014-12-05 | 2016-12-31 | USD |  | 500
| 2015-02-17 | 2019-02-17 | USD |  | 5300
Dairy Modernization and Market Access Programme - DiMMA (IFAD) | 2019-01-21 | 2025-12-31 | EUR | 16000 |  | 3600 |  | 119.7636 |  | 119.7636 |  | Development of value chain production / processing /sale and promotion of innovation in this sector. Institutional and organizational development; The program will be implemented in three regions: Imereti, Samegrelo-Zemo Svaneti and Samtskhe-Javakheti. Component 1 - Development of the dairy value chain: - 478 applications were submitted for the month of May, they are being processed; - A competition was announced to select a service provider that will organize demonstration plots in the target regions and conduct training for farmers employed in the dairy sector; - A competition was announced to select local coordinators for new regions added to the program (Kakheti, Kvemo Kartli, Racha-Lechkhumi and Kvemo Svaneti regions). Component 2 - Institutional Development: -The process of basic program research is completed.
Irrigation and Land Market Development Project (WB) | 2014-11-21 | 2021-07-31 | SDR | 32400 |  | 20000 |  | 853.0529 |  | 53606.6874 |  | Rehabilitation and Modernisation of irrigation and drainage services in selected areas: Kvemo Samgori Irrigation channel (2200 ha); Tbisi - Kumisi Irrigation channel (2200 ha) and Zeda Ru Irrigation channel (1319 ha) (ongoing). The estimated cost of project is 30.8 million SDR.
| 2020-03-30 |  | EUR | 18200 |  | 14000 |  | 382.9897 |  | 6170.8126 |  | In several pilot locations (including Shuakhevi, Vani, Martvili, Mestia, Dedoplistskaro, Gurjaani, Gori, Mtskheta, Tianeti, Tetritskaro) activities regarding land registration are ongoing. The estimated cost is 1.6 million SDR.
Environment Protection | [5 empty] | 0 | 4600 | 0 | 875.5366 | 0 | 27147.971
Development of Protected Areas (CNF) | 2009-11-02 | 2020-12-31 | EUR |  | 2267 | 0 | 2500 |  | 240.0252 |  | 7693.0453 | Support to: - Borjomi-Kharagauli National Park; - Lagodekhi Protected Area; - Vashlovani Protected Area; - Tusheti Protected Area. (Assessment of Borjomi-Kharagauli's "Sakhvlari" pasture is prepared, Tourism Strategy development for Borjomi-Kharagauli and Javakheti is completed; Small commerce/souvenir stall project in Administration of Borjomi is finished; Article on Javakheti and Lagodekhi for Journal "The Georgian" is finished, which was presented in tourism exhibition in Germany).
Support Programme for Protected Areas in the Caucasus - Georgia (Ecoregional Programme Georgia, Phase III) (KfW) | 2011-02-15 | 2020-10-31 | EUR |  | 8250 | 0 | 2100 |  | 635.5114 |  | 19454.9257 | - Construction of Administrative and Visitor Centers of Kazbegi, Kintrishi, Algeti Protected Areas was completed; - Eco-tourism strategies of Kazbegi, Kintrishi, Algeti and Pshav-Khevsureti are developed; - Management plans for Kazbegi, Kintrishi, Algeti and Pshav-Khevsureti are developed and prepared for approval; - Construction of Pshav-Khevsureti Administration and Visitor Center is ongoing; - Rehabilitation of Manglisi Roche Park is completing; - The demarcation of Pshav-Khevsureti is completed; - The physical demarcation of Kazbegi, Kintrishi, Algeti and Pshav-Khevsureti is completed; -The Prometheus Cave Exhibition space was fully rehabilitated; - A rope park was set up in Manglisi, Algeti National Park.
Other | [5 empty] | 171900 | 5050 | 7171.0963 | 15257.5 | 244256.0315 | 15257.5
Georgia I2Q - Innovation, Inclusion and Quality Project (IBRD) | 2019-06-18 | 2026-03-31 | EUR | 90000 |  | 5000 |  | 129.8239 |  | 129.8239 |  | To expand access to preschool education and improve the quality of education and learning environments.
GRANT - KfW - Economic Integration, Housing and Social Infrastructure for IDPs and Host Communities | 2019-01-28 | 2022-12-31 | EUR | 10000 |  | 0 | 0 |  | 15257.5 |  | 15257.5 | - A total of 236 houses will be built in Georgia on the land plots owned by internally displaced families. A village settlement will be created in Marneuli for internally displaced families. - 24 small scale infrastructural projects will be implemented near the settlements where the internally displaced people live. Eight new kindergarten will be built and two preschool facilities will be renovated. - A total of 236 grants will be issued in order to give source of income to the families moved to the new living area. - 130 business grants will be issued to small and medium sized enterprises to create job places for internally displaced people. About 260 young internally displaced person will undergo the professional qualification courses. Also, in western Georgia educational cetnres will be built for improving professional education and skills for internally displaced people.
Vocational Education Programme I (KfW) | 2019-06-14 | 2023-03-15 | EUR | 20000 |  | 1300 | 1900 |  |  | 0 | 0 | Construction of a Centre of Excellence, including equiping of classrooms and workshops and making small investmens in existing vocational colleges.
Rehabilitation of Tbilisi Public Schools and Energy Efficiency Improvement Project (CEB, E5P) | 2016-10-18 | 2021-06-30 | EUR | 14000 |  | 6100 | 1500 | 237.0919 |  | 237.0919 | 0 | Reconstruction - Rehabilitation and necessary efficiency improvements of approximately 25 public schools in Tbilisi. (preparatory works are ongoing).
Capacity building of the Georgian Armed forces (France - SG) | 2015-12-08 | 2018-05-08 | EUR | 82821 |  | 35000 |  |  |  | 226048.3489 |  | Capacity building of the Georgian Armed forces (France - SG) (ongoing)
Batumi Bus Project (EBRD, E5P) | 2017-07-13 | 2020-07-13 | EUR | 5500 | 1500 | 2500 | 1650 |  |  | 8749.2804 | 0 | - Purchasing of buses (diesel and electric). 40 units of diesel buses were purchased and brought to Georgia; - Purchasing of electric buses (planned).
Tbilisi Bus Project - Phasa-II (EBRD, E5P) | 29.11.2019 | 20.12.2022 |  |  |  | 100000 |  | 2337.4 |  |  |  | Planned
National Innovation Ecosystem Project (IBRD) | 2016-03-28 | 2021-04-30 | USD | 23500 |  | 20000 |  | 4460.5305 |  | 9085.2364 |  | - Development of a network of Innovation Hubs and Innovation Centers in the various cities and villages of Georgia; - Support to increase adoption and use of broadband internet services and advanced information technology by Eligible Households and Eligible MSMEs in rural areas of Georgia; - Developing the innovation capacity of individuals and firms.
Applied Research Grants Program (National Innovation Ecosystem Project) (IBRD) | [5 empty] | 2000 |  | 6.25 |  | 6.25 |  | Providing Applied Research Grants to scientists selected through the Shota Rustaveli National Science Foundation.
[5 empty] | Total | 1182300 | 46900 | 396957.7666 | 23802.0802 | 5304088.2804 | 249542.773
*The Projects financed under the several financing agreement, that have been concluded in different period of time, the date of the first financing agreement is indicated.
** The amount of expenditures made from the commercial bank accounts, may be revised at a later stage.
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0