## For Website_ENG
Donors’ supported Projects Envisaged in the State Budget
As of January 31, 2019 (In thousand)
Projects | Date of Agreement* | Project Closing date | Agreed amount |  |  | Amount envisaged in the State Budget 2019 |  | Expenditures made during the Year of 2019 (Actual expenditures) ** |  | Total of Expenditures (Actual expenditures) ** |  | Comment
|  |  | Currency of Loan/Grant |  |  | GEL |  | GEL |  | GEL
|  |  | Currency | Credit | Grant | Credit | Grant | Credit | Grant | Credit | Grant
Road Infrastructure | [5 empty] | 680550 | 8050 | 244.6588 | 16.2591 | 2002743.569 | 31012.1085
Fourth East-West Highway Improvement Project (Agara - Zemo Osiauri) (WB) | 2013-06-06 | 2019-02-28 | SDR | 24500 |  | 4000 |  | 33.2273 |  | 148892.5109 |  | - Construction of the Agara - Zemo Osiauri Section (approximately 12 km) of the Highway (construction works are completed, 7 km section is open for traffic, the remaining 5 km section will be opened after the completion of construction works on the section of Zemo Osiauri-Chumateleti ) - Construction of a riverbank protection (approximately 3.4 km) structure (completed); - Feasibility study and other preparatory activities (including Second Rikoti Tunnel) for the construction of the Rikoti-Zestafoni Section of Highway (completed).
|  |  | USD | 38000
East-West Highway Corridor Improvement Project (Zemo Osiauri - Rikoti) (WB, EIB) | 2016-02-10 | 2020-12-31 | USD | 140000 |  | 55225 |  | 7 |  | 102583.2369 |  | - Construction of the Zemo Osiauri - Chumateleti Section (approximately 14.1 km) of the Highway ( construction works are ongoing for Lot I, agreement for Lot II was terminated, the legal procedures are ongoing); - Providing support for capacity building to the Roads Department of Georgia (planned); - Technical Assistance to the Ministry of Economy and Sustainable Development of Georgia in preparation of Feasibility Study to identify priority logistic sites (completed); - Preparation of designs and supporting studies for future investment for the development of the road network (planned).
|  |  | EUR | 49450
Road Corridor Investment Program (Kobuleti Bypass Road) (ADB) | 2009-10-29 | 2019-09-29 | SDR | 75892 |  | 4000 |  | 37.576 |  | 372867.4382 |  | Construction of a new Kobuleti Bypass Road (approximately 32 km) (First section (12.4 + 1.3 km) of the Highway is open for traffic, construction works completed for second section (18 km), traffic is open).
|  |  | USD | 140000
Batumi New Bypass Road (ADB, AIIB) | 12.06.2017 | 30.06.2023 | EUR | 108190 |  | 56000 |  |  |  | 61088.3964 |  | - Construction of Batumi Bypass two-lane 14.3 km Road (construction works are ongoing); - Maintenance of approximately 200 km International and Local roads (planned).
|  |  | USD | 114000
East-West Highway Improvement Project (Zestafoni - Kutaisi - Samtredia) (JICA) | 2009-12-16 | 2023-06-24 | JPY | 22132000 |  | 1600 |  |  |  | 395400.0516 |  | - Construction of Zestafoni - Kutaisi section (15.2 km) (Construction works are ongoing, 14 km section is open for traffic); - Construction of a new Kutaisi bypass (Construction works completed for 17.3 km section of the Highway and was opened for traffic in 2014); - Construction of a new road from Kutaisi to Samtredia (Construction works are completed and 24 km section is open for traffic).
East-West Highway Improvement Project (Samtredia-Grigoleti-Kobuleti) (EIB, EU) | 2012-05-11 | 2019-11-28 | EUR | 200000 | 20000 | 52300 | 8050 | 119.2335 | 16.2591 | 299818.0252 | 31012.1085 | - Construction of a new four lane highway (approx. 52 km) from Samtredia to Grigoleti (construction works are going under the II, III და IV lots, the contract was signed with the winner construction company for remaining works under I lot, the mobilization and construction works started); - Road sections of Poti-Grigoleti and Grigoleti-Kobuleti Bypass Road ( preparation of the Detailed Design was completed);
Construction-Rehabilitaion of Chumateleti-Khevi section of Tbilisi-Senaki-Leselidze Road (WB, EIB) | 04.2.2017 | 31.12.2023 | EUR | 16000 |  | 45600 |  |  |  | 125.7445 |  | Upgrading of approximately 11 km of the existing 2-line East-West Highway Corridor to a 2-line dual carriageway from Chumateleti to Khevi; ( the tender for construction works was announced on the 8th of November 2018). The project will be implemented by EIB co-financing.
Consturction-Rehabilitation of Khevi-Ubisa section of Tbilisi-Senaki-Leselidze Road (ADB) | 2018-10-05 | 2024-12-31 | EUR | 255.297 |  | 63550 |  |  |  | 113756.3746 |  | Construction-Rehabilitaion of Chumateleti-Khevi section of Tbilisi-Senaki-Leselidze Road ( the contract was signed with the winner construction company).
Construction-Rehabilitation of Ubisa-Dzirula section of Tbilisi-Senaki-Leselidze Road (EIB) | 2016-10-09 | 2021-12-09 | EUR | 250 |  | 96850 |  |  |  | 201682.0098 |  | Consturction-Rehabilitation of Khevi-Ubisa section of Tbilisi-Senaki-Leselidze Road (Tendering procedures are ongoing).
Construction-Rehabilitation of Dzirula-Argveta section of Tbilisi-Senaki-Leselidze Road (JICA) | [5 empty] | 48850 | [5 empty] | Construction-Rehabilitation of Dzirula-Argveta section of Tbilisi-Senaki-Leselidze Road (Approval from the donor for tender disruption is received).
Construction of Grigoleti-Choloki (km48 - km64) section of Senaki-Poti-Sarpi Road (EIB) | [5 empty] | 48700 |  |  |  | 20357.4038 |  | Construction of Grigoleti-Choloki (km48 - km64) section of Senaki-Poti-Sarpi Road (the contract was signed with the winner construction company on the third of december 2018).
Construction of Rustavi-Red Bridge (km22 - km57) section of Tbilisi-Red Bridge (Border of Republic of Azerbaijan) Road (EIB) | [11 empty] | Construction of Rustavi-Red Bridge (km22 - km57) section of Tbilisi-Red Bridge (Border of Republic of Azerbaijan) (planned).
Construction/Upgrading of Algeti-Sadakhlo Road (EIB) | [11 empty] | Construction/Upgrading of Algeti-Sadakhlo Road (planned)
Construction of road and tunnel on Kvesheti-Kobi section of Mtskheta-Stepantsminda-Larsi Road (ADB) | [5 empty] | 122275 | [5 empty] | Construction of road and tunnel on Kvesheti-Kobi section of Mtskheta-Stepantsminda-Larsi Road ( Tendering procedures are ongoing for selecting the constructors and contractors; The announcement of the tender is scheduled at the end of February).
Construction of Poti Bridge on River Rioni (EIB) | [11 empty] | Construction of Poti Bridge on River Rioni (planned).
Construction of Lochini-Sagarejo (km20-km50) section of Tbilisi-Bakurtsikhe-Lagodekhi Road (EIB) | [11 empty] | Construction of Lochini-Sagarejo (km20-km50) section of Tbilisi-Bakurtsikhe-Lagodekhi Road (planned).
Second Secondary and Local Roads Project (SLRP II) (WB) | 2012-03-22 | 2019-06-30 | SDR | 25800 |  | 2300 |  | 4.5 |  | 126591.1824 |  | Rehabilitation of secondary and local roads in different regions of Georgia (approx. 225 km in total) (completed).
|  |  | USD | 30000
Third Secondary and Local Roads Project (SLRP III) (WB) | 2014-07-09 | 2020-06-30 | USD | 75000 |  | 32000 |  | 18.6205 |  | 111251.2833 |  | Rehabilitation of secondary and local roads in different regions of Georgia (approx. 200 km in total) (an additional 12 road will be rehabilitated within the project (approx. 80 km in total), the contracts were signed for the rehabilitation of 8 road sections and the rehabilitaton works are ongoing, the tendering procedures for selecting the contractor-construction companies for rehabilitation of 4 road secions are ongoing).
Secondary Road Asset Management Project (WB) | 2016-03-28 | 2021-12-31 | USD | 40000 |  | 20000 |  |  |  | 31603.9207 |  | - Rehabilitation and/or periodic maintenance, technical works of selected secondary road sections in Guria region (planned); - Rehabilitation of selected secondary road sections in Mtskheta - Mtianeti, Racha - Lechkhumi and Shida Kartli regions considering the design and construction conditions (project and rehabilitation works are ongoing); -Monitoring and supervision of works contracts (supervision of rehabilitation works of 4 road sections is ongoing).
Construction-Rehabilitation of Chumateleti-Kharagauli section of Secondary Dzirula-Kharagauli-Moliti-Pona-Chumateleti Road (ADB) | 19,06,2017 | 31.08.2021 | USD | 80000 |  | 15400 |  | 4.6386 |  | 15773.7666 |  | Rehabilitation of secondary road connecting Dzirula-Kharagauli-Moliti-Pona-Chumateleti Road ( Dzirula-Moliti road rehabilitation - the constraction works are ongoing; the contract was signed with the winner construction company for rehabilitation of Moliti-Chumateeti road section).
Batumi-Akhaltsikhe Road Project (Khulo-Goderdzi Section) (Kuwait Fund) | 2017-01-17 | 2020-12-31 | KWD | 8000 |  | 9200 |  | 19.8629 |  | 815.1691 |  | Rehabilitation-reconstruction of the Khulo-Goderdzi Section of the Batumi-Akhaltsikhe Road Project (approximately 29 km 2 lane road) (Instructions for starting works were issued).
Sadakhlo - Bagratashen Bridge Project (EBRD) | 2016-12-30 | 2019-12-31 | EUR | 6000 |  | 2700 |  |  |  | 137.055 |  | Construction of a new bridge at the Sadakhlo-Bagratashen border crossing between the Republic of Armenia and Georgia (preparatory and project works started).
Urban and Municipal Infrastructure | [5 empty] | 211480 | 7100 | 1582.0616 | 2.0592 | 742159.3315 | 14891.0851
Second Regional and Municipal Infrastructure Development Project (WB) | 2014-08-18 | 2019-06-30 | USD | 30000 | 5000 | 8800 | 3600 | 435.6442 | 2.0592 | 42986.0527 | 4760.8049 | Small size infrastructural projects in various regions of Georgia (rehabilitation of roads, streets, water-pipes, sewerage system) (construction works are ongoing).
Adjara Solid Waste Project (EBRD) | 2010-02-18 | 2018-12-31 | EUR | 3000 |  | 3000 |  |  |  | 74.757 |  | -Construction of a new, modern solid waste landfill in Adjara (Kobuleti, near Tsetskhlauri village; Preparatory activities are ongoing); - Closure of the existing solid waste landfill in Batumi (to be closed once a new solid waste landfill becomes operational).
Kutaisi Solid Waste Project (KfW, EU) | 2013-12-13 | 2018-12-31 | EUR | 20000 | 2000 | 15000 | 1000 |  |  | 7439.8587 | 4849.8896 | - Construction of a new solid waste landfill (Kutaisi entrance, Chognari Village) (preparatory works are ongoing); - Purchasing of necessary machinery/equipment for the transportation of solid waste and functioning of the sanitary landfill (planned in 2017); - Closure of the existing solid waste landfill in Kutaisi (to be closed once a new solid waste landfill becomes operational).
Sustainable Urban Transport Investment Program (ADB) | 2010-06-21 | 2020-07-18 | SDR | 68625 |  | 59650 |  | 56.6922 |  | 358812.8908 |  | - Rehabilitation of Zugdidi-Mestia road (completed); - Anaklia coastal protection Phase I (Completed); - Construction of a new subway station "University" in Tbilisi (completed); - Construction of Tbilisi-Rustavi highway Sections I - II (completed); - Construction of Tbilisi-Rustavi highway Section II (construction works are ongoing); - Coastal protection of Anaklia Phase II (completed); - Construction of a coastal protection works in Batumi (construction works are ongoing); - Rehabiliotation of subway station in Tbilisi ( replacement of subway electrical and ventilation system) (construction works are ongoing).
|  |  | USD | 141886
First Regional Development Project (Kakheti) (WB) | 2012-03-28 | 2018-10-30 | USD | 60000 |  | 30 |  |  |  | 102881.3544 |  | - Rehabilitation of infrastructure in Telavi, Kvareli and Akhmeta (municipal and communal infrastructure, rehabilitation of historical districts) (main works completed); - Rehabilitation and improvement of cultural heritage sites (supportive infrastructure) in the Kakheti region (main works completed); - Support for private sector in Agriculture and Tourism (completed).
Second Regional Development Project (Imereti) (WB) | 2012-11-09 | 2019-12-31 | SDR | 19800 |  | 8500 |  | 359.8691 |  | 58027.5978 |  | - Rehabilitation of infrastructure in Tskaltubo; - Rehabilitation and improvement of cultural heritage sites in Imereti region (supportive infrastructure) (constructions works are ongoing).
|  |  | USD | 9000
Third Regional Development Project (Samtskhe-Javakheti and Mtskheta-Mtianeti) (WB) | 2015-08-07 | 2019-12-31 | USD | 60000 |  | 24000 |  | 46.6651 |  | 31148.3938 |  | Rehabilitation of infrastructure and improvement of cultural heritage sites in Samtskhe-Javakheti and Mtskheta-Mtianeti (construction works are ongoing).
Kvemo Kartli Solid Waste Project (EBRD, SIDA) | 2015-05-12 | 2018-05-12 | EUR | 4300 | 1843 | 1000 |  |  |  | 119.7894 |  | Construction of new landfill in the Kvemo Kartli Region (in the city of Marneuli) (preparatory works are ongoing).
Georgia Solid Waste Management Project (EBRD) | 2016-07-12 | 2017-10-28 | EUR | 10000 | 2000 |  | 500 |  |  | 12332.7631 | 5280.3906 | Purchase of a new fleet of solid waste collection vehicles and solid waste containers (ongoing, approximately 150 waste-disposal vehicles and 7200 solid waste containers were purchased and given to municipalities).
Energy Efficiency Improvements in Public Buildings and Use Renewables and Alternatuve Energy in Georgia (NEFCO , E5P) | 2018-07-04 | 2020-07-04 | EUR | 2830 | 1870 | 3000 | 1000 |  |  |  |  | Planned
Georgia Urban Reconstruction and Development FL (EIB) | 2016-02-11 | 2021-02-11 | EUR | 100000 |  | 59500 |  | 683.1908 |  | 128335.8739 |  | - Small size infrastructural projects in various regions of Georgia (rehabilitation of roads, streets, water-pipes, sewerage system); - Rehabilitation/construction of the infrastructure damaged after the flooding in Tbilisi in 2015 (construction works are ongoing)
Georgia Upgrade of Municipal Infrastructure (EIB) | 2016-12-09 | 2021-12-31 | EUR | 100000 |  | 8000 | [5 empty] | - Small size infrastructural projects in various regions of Georgia (rehabilitation of roads, streets, water-pipes, sewerage system); - Rehabilitation/construction of the infrastructure damaged after the flooding in Tbilisi in 2015 (construction works are ongoing)
Integrated Solid Waste Management Program II (Kakheti and Samegrelo - Zemo Svaneti.) (KfW) | 2017-10-27 | 2022-12-30 | EUR | 30000 | 2000 | 1000 | 1000 |  |  |  |  | To implement an environmentally and hygienically sound solid waste management system for regions Kakheti and Samegrelo - Zemo Svaneti.
EBRD - Tbilisi Solid Waste Project | 1900-01-26 02:41 | 1900-01-26 02:41 | EUR | 15000 |  | 20000 | [5 empty] | - Renewing the Solid Waste collection fleet (rear loaded compactor vehicles); - Upgrading of the existing solid waste transfer station; - Rehabilitation and Improvement of the leachate system at the solid waste landfill of Tbilisi.
Water Infrastructure | [5 empty] | 156290 | 11695 | 4050.1533 | 347.0854 | 671423.6279 | 97967.5075
Kobuleti Wastewater Project (EBRD, ORET) | 2008-06-27 | 2018-09-30 | EUR | 3700 | 1814 | 1500 |  |  |  | 6580.4614 | 3649.681 | Rehabilitation of wastewater collector and treatment plant in Kobuleti (ongoing).
Urban Services Improvement Investment Program (Water Supply and Sewage Sector) (ADB) | 2011-05-10 | 2019-09-30 | SDR | 163600 |  | 122700 |  | 3397.1962 |  | 494759.3008 |  | -Mestia - Construction of Water Intake building (completed);Construction/rehabilitation of water supply and wastewater networks (construction works are completed); Construction of wastewater treatment plant and new reservoir, rehabilitation of existing reservoir (design-build is ongoing); -Anaklia - Construction of Water Intake building; Construction/rehabilitation of water supply and wastewater networks (completed); construction of wastewater treatment plant (the storage procedures are ongoing); - Kutaisi - Construction/rehabilitation of water supply systems (reservoirs, pumping stations, water distribution network) (construction works are ongoing); - Poti - Construction/rehabilitation of water supply systems (completed); rehabilitation of wastewater network (constructio works are ongoing); rehabilitation of wastewater treatment plant (Soil reinforcement works are ongoing); - Ureki - Construction of water supply and wastewater systems (water distribution network, wastewater collector and treatment plant) (construction works are ongoing); - Ureki - Construction of wastewater collector and treatment plant (the storage procedures are ongoing); - Zugdidi - Construction of water systems (construction works are ongoing); - Zugdidi - Construction/rehabilitation of wastewater systems (construction works are ongoing); - Zugdidi - Construction of water supply and wastewater systems (the procedures for selection of the design are ongoing); - Jvari – Construction of Water Supply System (construction works are ongoing); - Chiatura - Construction of Water Supply System (construction works are ongoing); - Marneuli - Rehabilitation of water supply and wastewater system facilities ( the mobilization works are ongoing) - Construction of Abasha main line (constructions works are ongoing). - Construction of Water Supply System in Telavi (assessment procedures are ongoing); - Construction water and sewerage systems in Gudauri (the contract is signed) - Constraction of wastewater treatment plant in Gudauri (tender procedures are ongoing).
|  |  | USD | 250000
Kutaisi Waste Water (EIB, EPTATF) | 15,10,2015 | 15,10,2020 | EUR | 100 |  |  | 2500 |  |  | 35.078 |  | Kutaisi - Construction/rehabilitation of water supply systems and treatment Plant (the procedures of designing of construction works and supervisory service procurement are ongoing).
Rehabilitation of Municipal Infrastructure Facilities in Batumi - Phase III (KfW, EU-NIF) | 2011-08-18 | 2019-12-31 | EUR | 26988.339 | 31228.536 | 18400 | 2850 |  |  | 46200.7648 | 57507.5065 | - Rehabilitation of water supply and sewerage systems network in Batumi (activities are partially completed); - Construction/rehabilitation of water reservoirs (completed); - Construction-rehabilitation of treatment plants (completed); - Creation of a sewerage system in the coastal villages of Adjara, in particular Gonio, Kvariati, Sarfi and Akhalsofeli (completed); - Modernization of the existing water supply infrastructure and provision of decentralized water supply systems In three villages surrounding Batumi (Chakvi, Mtsvane Kontskhi and Makhinjauri) (ongoing); -Installation of water meters in Batumi (works are ongoing).
Rehabilitation of Municipal Infrastructure Facilities in Batumi - Phase IV (KfW, EU) | 2015-12-22 | 2020-06-30 | EUR | 30000 | 2000 | 9690 | 4345 |  |  | 34681.4911 | 3499.0414 | Rehabilitation and extension of water supply and wastewater system facilities in Batumi (ongoing).
Water Infrastructure Modernisation Project II (EIB, EU) | 2013-08-20 | 2018-08-20 | EUR | 40000 | 8000 | 4000 | 700 | 652.9571 | 347.0854 | 89166.5317 | 18167.5967 | Improvement of water supply system in various regions of Georgia (ongoing).
Supporting Sustainable Wastewater Management (SIDA) | 2013-07-25 | 2020-02-28 | USD |  | 10052.155 |  | 1300 |  |  |  | 15143.6818 | Construction of the wastewater treatment plants in Tskaltubo and Telavi (construction works are ongoing).
Energy Infrastructure | [5 empty] | 86600 | 14000 | 1391.0421 | 0 | 259594.7677 | 20950.6801
Enguri Hydro Power Plant Rehabilitation Project - Climate Resilience Upgrade (EBRD, EU) | 2018-01-05 | 31,12,2021 | EUR | 28000 | 7000 | 15000 | 10000 | 238.3819 |  | 2826.6596 |  | - The project aims to make improvements to the Enguri HPP to alleviate critical power shortages in Georgia at a low cost and to enhance the environmental benefits of the Enguri HPP facility. - New EBRD loan will also help to improve the climatic conditions on the HPP territory. (preparatory works are ongoing).
Transmission Line Project - 500-220 kv "Jvari - Khorga" (EBRD, KfW, EU) | 2013-10-25 | 2018-12-29 | EUR | 60200 | 8000 | 6400 |  |  |  | 92412.662 | 20950.6801 | - Construction of the electricity lines from the Kavkasioni Transmission Line to the Jvari substation and between the Jvari and the Khorga substations (ongoing); - Construction of Transmission Lines connecting Ksani and Stepantsminda substations (500 Kv) (ongoing) .
Transmission Line Project - 500 kv "Ksani - Stefanwminda" ( KfW). | [5 empty] | 4700 |  | 1152.6602 |  | 46372.5505
250MGvar reactor in substation "Zestafoni"(EBRD) | [9 empty] | 5120.6747 |  | Constructing of 250 Mgvar capacity reactor in substation "Zestafoni 500" (planned).
Transmission Line Project -500 kv Tskaltubo -Akhaltsikhe - Tortumi (KfW) | 2017-04-13 | 2022-06-30 | EUR | 125000 |  | 5000 | 4000 |  |  |  |  | - Construction of 500kV double-circuit OHL Tskaltubo-Akhaltsikhe) - Extension of 500kV substation Akhaltsikhe; - Construction of 400kV OHL Akhaltsikhe-Tortum (planned)
Transmission Grid Strengthening Project - 220kv "Akhaltsikhe - Batumi" (WB) | 2014-09-03 | 2019-03-31 | USD | 60000 |  | 10000 |  |  |  | 112430.3023 |  | Construction of high voltage Electricity Transmission Line (220kv) from Akhaltsikhe to Batumi (142km) (ongoing). At this stage consultations are ongoing with the donor in order to replace certain works and the completion date within the project, to reflect the changes in the Loan Agreement regarding the project implementation unit due to the merging of the Ministries of Energy and Environmental Protection. The Amendment to the Agreement will be submitted to the Parliament for ratification.
Georgian Electricity Sector Development (WB) |  |  | USD | [6 empty] | 431.9186 |  | Electricity Sector Strategic Environmental and Social Assessment.
North Ring – Tskaltubo (Phase 1) (EBRD, KfW) |  |  | EUR |  |  | 13500 | [5 empty] | - Construction of 220kV double-circuit OHL Khudoni-Nenskra; - Construction 110kV OHL Khudoni-Mestia; - Construction of 125MVA, 110/35kV SS Mestia; - Construction of 500/220/110kV SS Khudoni; - 500kV OHL Kavkasioni tie-in to SS Khudoni; - Construction of 110kV double circuit OHL Kheledula-Jakhunderi; - Construction/Extension of 220kV SS Lajanuri (planned)
500Kv OHL Jvari –Tskhaltubo (WB) |  |  | USD |  |  | 9000 | [5 empty] | - Construction of 500kV single-circuit OHL Jvari – Tskhaltubo (approximately 100 Km); - Construction of 500kV SS Tskhaltubo (planned)
Reinforcement of Transmission Infrastructure of Guria (KfW) |  |  | EUR |  |  | 4500 | [5 empty] | - 220/110kV substation Ozurgeti, 250MVA installed capacity; - Double circuit OHL tie-in from 220kV OHL Paliastomi to 220/110kV substation Ozurgeti; - Construction of a new 110kV substation in Chokhatauri; - Construction of a new double-circuit 110kV line Ozurgeti-Chokhatauri (planned)
Strengthening Kakheti Infrastructureა (KfW) |  |  | EUR |  |  | 9500 | [5 empty] | Planned
Kheledula-Lajanuri-Oni (KfW) |  |  | EUR |  |  | 9000 | [5 empty] | Planned
Agriculture Sector | [5 empty] | 19830 | 4310 | 654.104 | 290.229 | 66499.6432 | 6893.7126
Agriculture Modernization, Market Access, and Resilience (GEF, IFAD) | 2015-02-17 | 2019-02-17 | SDR | 8610 |  | 6730 | 4070 | 389.5213 | 290.229 | 16668.5744 | 6392.7856 | upport for the growth of income of small farmers in various regions of Georgia and promote investments in the production / processing / sale of agricultural products - 4 demonstration plots for fruit trees,2 demonstration plots for vegetables and 3 demonstartion plots for berry plantation, 1 demonstation plot for bay-tree, demonstration plots for 1 conservative agriculture and 2 storehouses of windmill in Kakheti, Shida Kartli, Adjara and Samegrelo regions were arranged. At this stage 44 trainings (theoretical and practical trainin) were arranged for 2398 participants. - 337 small and large size grants were issued (350 for enterprises ad 7 for processing enterprises); - Rehabilitation of distribution network for Tirifoni irrigation system in Gori Municipality is completed; - The rehabilitation of the main channel and internal networks of irrigation system in Dzevera-Shurtula is completed; - The procedures for preparing the detailed project for rehabilitation of the irrigation distribution system and network is ongoing (Kvemo Alazani, Saltvisi); - The contract was signed for rehabilitation / modernization of Qvemo Alazani irrigation system distribution channel; - The tender of the construction works is completed for the rehabilitation of small rural infrastructure (roads and bridges) in Shida Kartli (Kareli, Gori) and in Samegrelo (Khobi), tender proposals evaluation process is ongoing; - Rehabilitation of rural road is completed in Lagodekhi Municipality in village Giorgeti; - The detailed project for landscape restoration plan of river Charebula in Shida Kartli, Gori Municipality is prepared; - The landscape restoration plan, in particular Windmill Arrangement Plan is prepared in Shida Kartli, Gori Municipality, village Sakasheti.
| 2014-12-05 | 2016-12-31 | USD |  | 500
| 2015-02-17 | 2019-02-17 | USD |  | 5300
Irrigation and Land Market Development Project (WB) | 2014-11-21 | 2021-07-31 | SDR | 32400 |  | 11000 |  | 78.8211 |  | 45260.6442 |  | Rehabilitation and Modernisation of irrigation and drainage services in selected areas: Kvemo Samgori Irrigation channel (2200 ha); Tbisi - Kumisi Irrigation channel (2200 ha) and Zeda Ru Irrigation channel (1319 ha) (ongoing). The estimated cost of project is 30.8 million SDR.
[6 empty] | 2100 |  | 185.7615 |  | 4570.4246 |  | In several pilot locations (including Shuakhevi, Vani, Martvili, Mestia, Dedoplistskaro, Gurjaani, Gori, Mtskheta, Tianeti, Tetritskaro) activities regarding land registration are ongoing. The estimated cost is 1.6 million SDR.
Rehabilitation of Zemo Samgori Irrigation System (ORIO) | 2014-11-03 | 2018-03-31 | EUR |  | 861 |  | 240 |  |  |  | 500.927 | - Rehabilitation of Zemo Samgori Irrigation System. Project Preparation Stage (Preparation stage for the necessary materials for the preparation of the relevant research and technical, social, environmental and institutional aspects of analysis is completed. The process of closing the project development phase is ongoing).
Environment Protection | [5 empty] | 0 | 4645 | 0 | 0 | 0 | 22062.834
Development of Protected Areas (CNF) | 2009-11-02 | 2018-12-31 | EUR |  | 2267 |  | 1345 |  |  |  | 6077.2089 | Support to: - Borjomi-Kharagauli National Park; - Lagodekhi Protected Area; - Vashlovani Protected Area; - Tusheti Protected Area. (Assessment of Borjomi-Kharagauli's "Sakhvlari" pasture is prepared, Tourism Strategy development for Borjomi-Kharagauli and Javakheti is completed; Small commerce/souvenir stall project in Administration of Borjomi is finished; Article on Javakheti and Lagodekhi for Journal "The Georgian" is finished, which was presented in tourism exhibition in Germany).
Support Programme for Protected Areas in the Caucasus - Georgia (Ecoregional Programme Georgia, Phase III) (KfW) | 2011-02-15 | 2017-12-31 | EUR |  | 8250 |  | 3300 |  |  |  | 15985.6251 | Creation of: - Kazbegi National Park; - Kintrishi Protected Area; - Algeti National Park; - Pshavi-Khevsureti Protected Area. (Development of tourism Action and Investment plans are ongoing; Development of Management Plan for Algeti National Park has commenced; Tender for demarcation of Pshavi-Khevsureti protected territories is announced; Construction of building for Algeti National Park administration and for visitors has commenced; Construction of building for Kazbegi National Park administration and for visitors has commenced; Arrangement of exhibition hall for Prometheus Cave is ongoing; Development of draft law for the creation of protected landscape in Dusheti municipality is ongoing).
Other | [5 empty] | 146300 | 42900 | 482.089 | 5156.8473 | 239904.4242 | 286955.7593
Millennium Challenge Georgia - Compact II (MCC) | 2012-07-13 | 2018-07-26 | USD |  | 142700 |  | 38900 |  | 5156.8473 |  | 286955.7593 | Repairs/rehabilitation of public schools in the regions of Georgia - Rehabilitation of 71 public schools and equipping with natural laboratories in Shida Kartli, Samtskhe-Javakheti, Racha-Lechkhumi and Kvemo Svaneti regions (completed); - Full rehabilitation of 20 public schools (is ongoing), 17 schools are located in western Georgia and 3 in Kakheti. Improvement of teacher's qualifications - In the framework of general professional training course 13,441 teachers were trained, including 1054 non-georgian language teacher. - Within the course of the subject methodology 14,153 teachers were trained, including 1054 non-georgian language teacher. Increase qualification of school directors - The project "Leadership Academy 1" and "Leadership Academy 2" has been completed for public school directors and facilitators, in total 1872 directors and 1,794 facilitators passed it successfully, including 190 non-georgian language school directors and 196 non-georgian language facilitators. Promotion of higher education in the technical field (ongoing) Complete rehabilitation of lecture rooms and laboratories, equipping and arrangement of new laboratories of San Diego State University (SDSU) partner universities of Georgia have been implemented.
Rehabilitation of Tbilisi Public Schools and Energy Efficiency Improvement Project (CEB, E5P) | 2016-10-18 | 2021-06-30 | EUR | 14000 |  | 1500 | 1000 |  |  |  | 0 | Reconstruction - Rehabilitation and necessary efficiency improvements of approximately 25 public schools in Tbilisi. (preparatory works are ongoing). At this stage the procedures of replacement the project implementing unit - Education and Science Infrastructure Development Agency with Municipal Development Found of Georgia is ongoing. Amendment to the loan agreement will be submitted to the Parliament of Georgia for ratification.
Capacity building of the Georgian Armed forces (France - SG) | 2015-12-08 | 2018-05-08 | EUR | 82821 |  | 55000 |  |  |  | 226048.3489 |  | Capacity building of the Georgian Armed forces (France - SG) (ongoing)
Batumi Bus Project (EBRD, E5P) | 2017-07-13 | 2019-12-31 | EUR | 5500 | 1500 | 4800 | 3000 |  |  | 8749.2804 | 0 | - Purchasing of buses (diesel and electric). 40 units of diesel buses were purchased and brought to Georgia; - Purchasing of electric buses (planned).
Tbilisi Bus Project - Phasa-II (EBRD, E5P) | [5 empty] | 75000 | [5 empty] | Planned
National Innovation Ecosystem Project (IBRD) | 2016-03-28 | 2021-04-30 | USD | 40000 |  | 10000 |  | 482.089 |  | 5106.7949 |  | - Development of a network of Innovation Hubs and Innovation Centers in the various cities and villages of Georgia; (the procedure for restructuring this component of the project is ongoing); - Support to increase adoption and use of broadband internet services and advanced information technology by Eligible Households and Eligible MSMEs in rural areas of Georgia (the procedure for restructuring this component of the project is ongoing); - Developing the innovation capacity of individuals and firms. (the procedure for restructuring this component of the project is ongoing);
[5 empty] | TOTAL | 1301050 | 92700 | 8404.1088 | 5812.4801 | 3982325.3634 | 480733.687
*The Projects financed under the several financing agreement, that have been concluded in different period of time, the date of the first financing agreement is indicated.
** The amount of expenditures made from the commercial bank accounts, may be revised at a later stage.
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0